## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Mahammadpur Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12654 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 13/RD/PHE | 03/01/2024 | 03/01/2024 | Resource Division | 1.42 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Mahammadpur Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12654 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Mahammadpur Piped Water Supply Scheme of Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer RWS HQ,Junior Engineer, RSD | ORD/000139/2022-2023 | 1917/RD/PHE | 28/10/2022 | 12/12/2022 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 34.87 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Mahammadpur Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12654 | Augmentation | Supply, installation, commissioning & trial operation of electro-mechanical components at T/W No. III of Source Augmentation of MAHAMMADPUR Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/002578/2023-2024 | 1004/MLMD | 11/03/2024 | 26/06/2026 | DAS CONSTRUCTION | 11.48 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Mahammadpur Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12654 | Augmentation | Quotation for new service connection at Source Aug for MAHAMMADPUR PH-III (Itahar ccc) in the district of Uttar Dinajpur (SM/12654). |  |  | BILL/02744/2024-2025 | BP-2024-25-623 | 06/02/2025 | 06/02/2025 | W.B.S.E.D.C.LTD | 6.27 | 0 | 0 | 0
Total | [13 empty] | 54.04 | 0 | 0