## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12655 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Goagaon Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer, RWS | ORD/000146/2022-2023 | 1924/RD/PHE | 28/10/2022 | 25/07/2023 | S. B. CONSTRUCTION | 33.07 | 9.79 | 29.6 | 25
2 | UTTAR DINAJPUR |  | Raiganj Division | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12655 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 2391/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.48 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12655 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Goagaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000320/2024-2025 | 2947/MLMD | 11/09/2024 | 30/01/2026 | SARADA MAA CONSTRUCTION. | 10.78 | 9.07 | 84.11 | 84
4 | UTTAR DINAJPUR |  | Malda Mechanical | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12655 | Augmentation | Quotation for new service connection at Source Augmentation of GOAGAON PH-III (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00229/2024-2025 | BP-2024-25-91 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 4.01 | 0 | 0 | 0
Total | [13 empty] | 50.34 | 18.85 | 37.45