## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | SM/12707 | New | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1118/RD/PHE | 24/04/2023 | 24/04/2023 | Resource Division | 29.16 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | SM/12707 | New | Quotation for new service connection at Angarbhasa PH-I (Goalpokher ccc). |  |  | BILL/03524/2023-2024 | BP-2023-24-544 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 9.41 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | SM/12707 | New | Additional Quotation for new service connection at ANGARBHASA PH-I (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12707) |  |  | BILL/00738/2024-2025 | BP-2024-25-216 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 0.72 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | SM/12707 | New | Quotation for new service connection at ANGARBHASA PH-II (Goalpokher ccc) in the district of Uttar Dinajpur. |  |  | BILL/03633/2023-2024 | BP-2023-24-617 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 22.5 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | SM/12707 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Angarbhasa Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/14458) | Assistant Engineer - I | Junior Engineer-02 | ORD/000353/2023-2024 | 2363/MLMD | 28/07/2023 | 27/04/2026 | MITRA ASSOCIATES | 25.36 | 0 | 0 | 72
6 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | SM/12707 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 6530.5 | 0 | 0 | 38
7 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | SM/12707 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 10/01/2025 | MD ZAFAR EQUEBAL | 2.6 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | SM/12707 | New | Laying of additional pipeline for improving FHTC at different mouzas at ANGARBHASA PWSS of Goalpokhar-I Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000258/2025-2026 | 2048/RD/PHE | 10/07/2025 | 06/01/2026 | ROY ENGINEERS. (PATNA) | 29.06 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | SM/12707 | New | Providing FHTC in connection with Angurbhasa Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000277/2025-2026 | 2182/RD/PHE | 29/07/2025 | 27/10/2025 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 5.79 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | SM/12707 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Angarbhasa Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 50 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000295/2025-2026 | 1923/RD/PHE | 30/06/2025 | 27/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.74 | 0 | 0 | 0
Total | [13 empty] | 6675.84 | 0 | 0