## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12778 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1122/RD/PHE | 24/04/2023 | 24/04/2023 | Resource Division | 41.33 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12778 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Athiala Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014486) | Assistant Engineer - I | Junior Engineer-02 | ORD/000401/2023-2024 | 2459/MLMD | 04/08/2023 | 27/01/2026 | JAL PRAVAHIKA PVT. LTD. | 28.11 | 0 | 0 | 63
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12778 | New | Quotation for new service connection at Athiala PH-II (Goalpokher ccc). |  |  | BILL/03523/2023-2024 | BP-2023-24-543 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 18.86 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12778 | New | Quotation for new service connection at Athiala PH-I (Goalpokher ccc) |  |  | BILL/03522/2023-2024 | BP-2023-24-542 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 18.09 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12778 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 6530.5 | 0 | 0 | 38
6 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12778 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
7 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12778 | New | Providing FHTC in connection with Athiala Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000034/2025-2026 | 1200/RD/PHE | 25/04/2025 | 25/05/2025 | DEEP CONSTRUCTION | 11.93 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12778 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at ATHIALA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000019/2025-2026 | 1203/RD/PHE | 25/04/2025 | 09/06/2025 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 40.92 | 0 | 0 | 0
Total | [13 empty] | 6694.53 | 0 | 0