## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Preparation & Submission of DPR for proposed Barhans Piped Water Supply Scheme under Karandighi Development Block. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000798/2021-2022 | 616/RD/PHE | 16/03/2022 | 15/04/2022 | ENVIROTECH SOLUTIONS | 3.11 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Preparation & Submission of DPR for Proposed Barhans Piped Water Supply Scheme under Karandighi block. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000804/2021-2022 | 616/RD/PHED | 16/03/2022 | 15/04/2022 | ENVIROTECH SOLUTIONS | 3.11 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Barhans PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001945/2023-2024 | 4003220342 | 07/09/2023 | 06/12/2023 | W.B.S.E.D.C.LTD | 5.38 | 0 | 0 | 100
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Barhans PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001946/2023-2024 | 4003220337 | 07/09/2023 | 06/12/2023 | W.B.S.E.D.C.LTD | 14.71 | 0 | 0 | 100
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 586/RD/PHE | 24/02/2023 | 24/02/2023 | Resource Division | 15.91 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 2352/RD/PHE | 11/08/2023 | 11/08/2023 | Resource Division | 16.43 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite at T/W no. I of Barhans Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014865) | Assistant Engineer - I | Junior Engineer-02 | ORD/000420/2023-2024 | 2471/MLMD | 04/08/2023 | 27/10/2025 | NIRMAN. | 24.86 | 0 | 0 | 72
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000626/2023-2024 | 472/RD/PHE | 28/02/2024 | 28/06/2024 | PRITAM SARKAR | 1.6 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARHANS PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000501/2023-2024 | 603/RD/PHE | 05/03/2024 | 28/02/2025 | M/S MAA BOLLA CONSTRUCTION | 22.57 | 0 | 0 | 100
10 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Additional Quotation for HT AB cable at BARHANS PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12779). |  |  | BILL/01110/2024-2025 | BP-2024-25-279 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 6.56 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Additional Quotation for new service connection at BARHANS PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12779) |  |  | BILL/02080/2024-2025 | BP-2024-25-486 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 3.4 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Implementation of BARHANS and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000221/2022-2023 | 99/RD/PHE | 19/01/2023 | 01/01/2027 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 271.31 | 0 | 0 | 62
13 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Barhans PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000449/2024-2025 | 3761/RD/PHED | 18/12/2024 | 17/01/2025 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 11.73 | 0 | 0 | 0
14 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000412/2024-2025 | 3446/RD/PHE | 26/11/2024 | 26/05/2025 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Barhans Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000339/2025-2026 | 2488/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 18.74 | 0 | 0 | 0
16 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12779 | New | Additional Laying distribution and Rising Main of Pipe line for Barhans Pipe Water Supply Scheme (Barhans New PWSS) at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000429/2023-2024 | 3393/RD/PHE | 12/12/2023 | 20/01/2025 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 7.87 | 0 | 0 | 100
Total | [13 empty] | 429.7 | 0 | 0