## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12780 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1126/RD/PHE | 24/04/2023 | 24/04/2023 | Resource Division | 36.82 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12780 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chhota Patna Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014398) | Assistant Engineer - I | Junior Engineer-02 | ORD/000467/2023-2024 | 2482/MLMD | 04/08/2023 | 21/03/2026 | MAA BHABOTARINE ENTERPRISE. | 27.46 | 0 | 0 | 73
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12780 | New | Quotation for new service connection at Choto Patna PH-I (Goalpokher ccc) |  |  | BILL/03521/2023-2024 | BP-2023-24-541 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 12.08 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12780 | New | Quotation for new service connection at Choto Patna PH-II (Goalpokher ccc) |  |  | BILL/03520/2023-2024 | BP-2023-24-540 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 10.71 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12780 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 6530.5 | 0 | 0 | 38
6 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12780 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at CHOTA PATNA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000017/2025-2026 | 1201/RD/PHE | 25/04/2025 | 09/06/2025 | HAQUE CONSTRUCTION | 39.32 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12780 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chotopatna Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000325/2025-2026 | 1996/RD/PHE | 07/07/2025 | 03/01/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 30.94 | 0 | 0 | 0
Total | [13 empty] | 6687.82 | 0 | 0