## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12782 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 1121/RD/PHE | 24/04/2023 | 24/04/2023 | Resource Division | 27.44 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12782 | New | Quotation for new service connection at Dakshin Sahapur PH-II (Goalpokher ccc) |  |  | BILL/03505/2023-2024 | BP-2023-24-525 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 4.17 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12782 | New | Quotation for new service connection at Dakshin Sahapur PH-I (Goalpokher ccc) |  |  | BILL/03504/2023-2024 | BP-2023-24-524 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 6.08 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12782 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dakshin Sahapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014427) | Assistant Engineer - I | Junior Engineer-02 | ORD/000355/2023-2024 | 2366/MLMD | 28/07/2023 | 26/06/2026 | WEST BENGAL ENGINEERING COMPANY. | 26.18 | 0 | 0 | 77
5 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12782 | New | Providing FHTC in connection with Dakhshin Sahapur Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000002/2025-2026 | 1175/RD/PHE | 23/04/2025 | 23/05/2025 | BIKASH KAR | 8.09 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12782 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshin Sahapur Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000344/2025-2026 | 1804/RD/PHE | 24/06/2025 | 21/12/2025 | JAL PRAVAHIKA PRIVATE LIMITED | 29.55 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12782 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at DAKSHIN SAHAPUR PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000382/2025-2026 | 2094/RD/PHE | 15/07/2025 | 11/01/2026 | M/S SACHIN KUMAR | 39.1 | 0 | 0 | 0
Total | [13 empty] | 140.61 | 0 | 0