## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12784 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Goalin Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014474) | Assistant Engineer - I |  | ORD/000541/2023-2024 | 2501/MLMD | 04/08/2023 | 02/12/2023 | A.G ENTERPRISE. | 29.41 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12784 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 11/08/2026 | ROY ENGINEERS. (PATNA) | 6530.5 | 0 | 0 | 38
3 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12784 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1125/RD/PHE | 24/04/2023 | 24/04/2023 | Resource Division | 43.9 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12784 | New | Additional pipeline, Pathway, Land development and other ancillary works at GOALIN piped water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000375/2025-2026 | 2289/RD/PHE | 12/08/2025 | 10/12/2025 | DEEP CONSTRUCTION | 78.53 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12784 | New | Providing FHTC in connection with Goalin Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000276/2025-2026 | 2181/RD/PHE | 29/07/2025 | 27/10/2025 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 6.17 | 0 | 0 | 0
Total | [13 empty] | 6688.51 | 0 | 0