## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | Preparation & Submission of DPR for proposed Gopalpur Piped Water Supply Scheme under Karandighi Development Block. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000799/2021-2022 | 602/RD/PHE | 15/03/2022 | 14/04/2022 | ENVIROTECH SOLUTIONS | 5.1 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | Preparation and submission of DPR for proposed Gopalpur PWSS under Karandighi block. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000805/2021-2022 | 602/RD/PHED | 15/03/2022 | 14/04/2022 | ENVIROTECH SOLUTIONS | 5.1 | 5.1 | 100 | 0
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | Implementation of GOPALPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000224/2022-2023 | 299/RD/PHE | 01/02/2023 | 01/04/2025 | UTTAM SAHA | 529.88 | 289.71 | 54.68 | 75
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head work site at T/W no. I of Gopalpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014866) | Assistant Engineer - I | Junior Engineer-02 | ORD/000537/2023-2024 | 2499/MLMD | 04/08/2023 | 02/12/2023 | A.G ENTERPRISE. | 29.23 | 24.44 | 83.6 | 84
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of GOPALPUR, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001558/2023-2024 | 4003220366 | 21/09/2023 | 20/12/2023 | W.B.S.E.D.C.LTD | 3.6 | 3.6 | 100 | 100
6 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of GOPALPUR, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001557/2023-2024 | 4003220371 | 21/09/2023 | 20/12/2023 | W.B.S.E.D.C.LTD | 3.7 | 3.7 | 100 | 100
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 584/RD/PHE | 24/02/2023 | 24/02/2023 | Resource Division | 33.67 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under GOPALPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000490/2023-2024 | 606/RD/PHE | 05/03/2024 | 19/04/2024 | M/S PRITHWIRAJ CONSTRUCTION | 22.58 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | Additional Pipe Line and other ancillary works to provide FHTC at GOPALPUR PWSS (New Scheme) under Islampur Sub-Division ,P.H.E. Dte. under Raiganj Division, PHED, Uttar Dinajpur. | Assistant Engineer ISD |  | ORD/000127/2024-2025 | 3018/RD/PHE | 03/10/2024 | 17/11/2024 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 27.54 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | Construction of concrete pathway ,Land development and other ancillary works for GOPALPUR Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000406/2024-2025 | 3576/RD/PHE | 05/12/2024 | 19/01/2025 | UTTAM SAHA | 20.94 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | Trial Run For Gopalpur PWSS under Karandighi Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000720/2024-2025 | 552/RD/PHE | 12/02/2025 | 13/05/2025 | UTTAM SAHA | 0.88 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Gopalpur Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000321/2025-2026 | 2481/RD/PHE | 12/09/2025 | 11/03/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.36 | 0 | 0 | 0
Total | [13 empty] | 714.57 | 326.55 | 45.7