## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12786 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jharbari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014422) | Assistant Engineer - I |  | ORD/000357/2023-2024 | 2368/MLMD | 28/07/2023 | 24/01/2024 | SUNRISE ENGINEERING CORPORATION. | 27.23 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12786 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1124/RD/PHE | 24/04/2023 | 24/04/2023 | Resource Division | 36.54 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12786 | New | Quotation for new service connection at JHARBARI PH-II (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00223/2024-2025 | BP-2024-25-89 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 6.69 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12786 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 6530.5 | 153.95 | 2.36 | 38
5 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12786 | New | Providing FHTC in connection with Jharbari Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000001/2025-2026 | 1176/RD/PHE | 23/04/2025 | 23/05/2025 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 12.6 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12786 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Jharbari Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000326/2025-2026 | 2012/RD/PHE | 08/07/2025 | 04/01/2026 | AJIT PRAMANIK | 30.93 | 0 | 0 | 0
Total | [13 empty] | 6644.49 | 153.95 | 2.32