## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12787 | New | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1123/RD/PHE | 24/04/2023 | 24/04/2023 | Resource Division | 23.6 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12787 | New | Quotation for new service connection at KAMALPUR PH-I (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12787) |  |  | BILL/01103/2024-2025 | BP-2024-25-278 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 13.21 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12787 | New | Quotation for new service connection at KAMALPUR PH-II (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12787) |  |  | BILL/01102/2024-2025 | BP-2024-25-277 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 3.62 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12787 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kamalpur Water Supply Scheme at Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 20 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000291/2025-2026 | 1818/RD/PHE | 24/06/2025 | 21/12/2025 | AJIT PRAMANIK | 15.38 | 0 | 0 | 0
Total | [13 empty] | 55.82 | 0 | 0