## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/12788 | New | Material Requisition To Resource Division |  |  | RTOR000119/2022-2023 | 614/RD/PHE | 28/02/2023 | 28/02/2023 | Resource Division | 29.14 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/12788 | New | Implementation of KAMLAGAON and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd Tube Well.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000300/2022-2023 | 549/RD/PHE | 23/02/2023 | 27/11/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 442.06 | 129.53 | 29.3 | 45
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/12788 | New | Laying of Additional Pipeline With landf development and path way for KAMLAGAON Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000416/2024-2025 | 3580/RD/PHE | 05/12/2024 | 19/01/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 80.34 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Islampur | Malda Mechanical | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/12788 | New | Quotation for new service connection at KAMLAGAON PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12788) |  |  | BILL/01090/2024-2025 | BP-2024-25-276 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 4.28 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Malda Mechanical | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/12788 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kamlagaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014738) | Assistant Engineer - I | Junior Engineer-02 | ORD/000519/2023-2024 | 2515/MLMD | 04/08/2023 | 26/03/2025 | SUJOY RANJAN BHOWMICK | 27.17 | 0 | 0 | 78
Total | [13 empty] | 582.99 | 129.53 | 22.22