## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12789 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1200/RD/PHE | 28/04/2023 | 28/04/2023 | Resource Division | 26.38 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12789 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kichaktola Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014974) | Assistant Engineer - I | Junior Engineer-02 | ORD/000516/2023-2024 | 2512/MLMD | 04/08/2023 | 29/10/2025 | SUBHAS CHANDRA KESHORI | 26.43 | 19.11 | 72.31 | 72
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12789 | New | Quotation for new service connection at KICHAKTALA PH-I (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00024/2024-2025 | BP-2024-25-51 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 7.74 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12789 | New | Quotation for new service connection at KICHAKTALA PH-II (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00025/2024-2025 | BP-2024-25-52 | 09/04/2024 | 09/04/2024 | W.B.S.E.D.C.LTD | 7.53 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12789 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 6530.5 | 170.38 | 2.61 | 38
6 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12789 | New | Providing FHTC in connection with Kichaktola Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000023/2025-2026 | 1178/RD/PHE | 23/04/2025 | 23/05/2025 | MAA SHEETALA ENTERPRISE | 12.76 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12789 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kichaktala Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000292/2025-2026 | 1825/RD/PHE | 25/06/2025 | 22/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.59 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12789 | New | Laying of additional pipeline for improving FHTCwith ancillary works at different mouzas at KICHAKTOLA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000264/2025-2026 | 2079/RD/PHE | 14/07/2025 | 10/01/2026 | ROY ENGINEERS. (PATNA) | 38.99 | 0 | 0 | 0
Total | [13 empty] | 6679.92 | 189.49 | 2.84