## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12790 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1204/RD/PHE | 28/04/2023 | 28/04/2023 | Resource Division | 2.69 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12790 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Pharabari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014703) | Assistant Engineer - I | Junior Engineer-02 | ORD/001967/2023-2024 | 3707/MLMD | 29/11/2023 | 27/05/2024 | SOVON KUMAR DAS. | 11.98 | 10.03 | 83.77 | 84
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12790 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of PHARABARI , Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02460/2023-2024 | BP-2023-24-392 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 18.12 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12790 | New | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 16.08.2024 & 20.08.2024. |  |  | BILL/00384/2024-2025 | BP-2024-25-224 | 04/10/2024 | 04/10/2024 | SAHA CONSTRUCTION | 0.06 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12790 | New | Implementation of Pharabari and it's adjoining mouzas Pipe Water Supply Scheme at Goalpokhar-I Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000289/2022-2023 | 536/RD/PHE | 22/02/2023 | 05/10/2024 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 43.62 | 42.68 | 97.83 | 100
Total | [13 empty] | 76.47 | 52.71 | 68.93