## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra | Malda Mechanical | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12791 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Purba Jaypura Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014442) | Assistant Engineer - I | Junior Engineer-02 | ORD/000533/2023-2024 | 2527/MLMD | 04/08/2023 | 26/06/2026 | M/S CHANDRANATH MUKHERJEE. | 26.16 | 5.01 | 19.15 | 72
2 | UTTAR DINAJPUR | Chopra | Raiganj Division | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12791 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 11/08/2026 | ROY ENGINEERS. (PATNA) | 7213.93 | 97.66 | 1.35 | 30
3 | UTTAR DINAJPUR | Chopra | Raiganj Division | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12791 | New | Material Requisition To Resource Division |  |  | RTOR000170/2022-2023 | 966/RD/PHE | 29/03/2023 | 29/03/2023 | Resource Division | 28.51 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Chopra | Malda Mechanical | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12791 | New | Quotation for new service connection at PURBA JAYPURA PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12791) |  |  | BILL/01079/2024-2025 | BP-2024-25-305 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 9.14 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Chopra | Malda Mechanical | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12791 | New | Quotation for new service connection at PURBA JAYPURA PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12791) |  |  | BILL/01078/2024-2025 | BP-2024-25-304 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 6.86 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Chopra | Raiganj Division | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12791 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Purba Joypura Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000298/2025-2026 | 1928/RD/PHE | 30/06/2025 | 27/12/2025 | MONDAL PRECISION PRIVATE LIMITED | 32.38 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Chopra | Raiganj Division | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12791 | New | Providing FHTC in connection with Purba Jaypura Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd call). | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000388/2025-2026 | 2170/RD/PHE | 25/07/2025 | 23/10/2025 | M/S SHIB ENTERPRISE | 6.63 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Chopra | Raiganj Division | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12791 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at PURBA JAYPURA PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000386/2025-2026 | 2098/RD/PHE | 15/07/2025 | 11/01/2026 | M/S SACHIN KUMAR | 56.82 | 0 | 0 | 0
Total | [13 empty] | 7380.43 | 102.67 | 1.39