## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12793 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1117/RD/PHE | 24/04/2023 | 24/04/2023 | Resource Division | 51.31 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12793 | New | Quotation for new service connection at Sholpara PH-II (Goalpokher ccc) in the district of Uttar Dinajpur. |  |  | BILL/03732/2023-2024 | BP-2023-24-695 | 15/03/2024 | 15/03/2024 | W.B.S.E.D.C.LTD | 10.3 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12793 | New | Quotation for new service connection at Sholpara PH-I (Goalpokher ccc) |  |  | BILL/03515/2023-2024 | BP-2023-24-535 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 4.65 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12793 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Sholpara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014404) | Assistant Engineer - I | Junior Engineer-02 | ORD/000767/2023-2024 | 2532/MLMD | 04/08/2023 | 27/05/2026 | M/S. KUNDU CONSTRACTION | 29.72 | 20.4 | 68.64 | 85
5 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12793 | New | Providing FHTC in connection with Solpara Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000022/2025-2026 | 1177/RD/PHE | 23/04/2025 | 23/05/2025 | CHAITANYA SAMAL | 10.15 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12793 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at SHOLPARA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000257/2025-2026 | 2047/RD/PHE | 10/07/2025 | 06/01/2026 | ROY ENGINEERS. (PATNA) | 52.51 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12793 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Sholpara Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000312/2025-2026 | 1979/RD/PHE | 03/07/2025 | 30/12/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.59 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12793 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 6530.5 | 218.39 | 3.34 | 38
Total | [13 empty] | 6722.72 | 238.79 | 3.55