## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra | Malda Mechanical | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12796 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uttar Mohangachh Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014503) | Assistant Engineer - I | Junior Engineer-02 | ORD/000552/2023-2024 | 2541/MLMD | 04/08/2023 | 19/07/2026 | SUBRATA SAHA | 25.68 | 18.36 | 71.47 | 72
2 | UTTAR DINAJPUR | Chopra | Raiganj Division | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12796 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 11/08/2026 | ROY ENGINEERS. (PATNA) | 7213.93 | 39.38 | 0.55 | 30
3 | UTTAR DINAJPUR | Chopra | Raiganj Division | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12796 | New | Material Requisition To Resource Division |  |  | RTOR000172/2022-2023 | 964/RD/PHE | 29/03/2023 | 29/03/2023 | Resource Division | 16.24 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Chopra | Malda Mechanical | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12796 | New | Quotation for new service connection at UTTAR MOHANGACHH PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12796) |  |  | BILL/01085/2024-2025 | BP-2024-25-274 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 4.02 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Chopra | Raiganj Division | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12796 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at UTTAR MOHANGACHH PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000016/2025-2026 | 1212/RD/PHE | 25/04/2025 | 09/06/2025 | K.G.N BUILDERS | 33.45 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Chopra | Raiganj Division | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12796 | New | Providing FHTC in connection with Uttar Mahangachh Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000274/2025-2026 | 2173/RD/PHE | 25/07/2025 | 23/10/2025 | RAKSHIT TRADERS | 8.37 | 0 | 0 | 0
Total | [13 empty] | 7301.69 | 57.74 | 0.79