## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13012 | New | Preparation & submission of DPR for proposed FATEPUR (Kantirpa-Fatepur) PWSS under Karandighi Block. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000802/2021-2022 | 617/RD/PHE | 16/03/2022 | 15/04/2022 | ECO CARE | 6.64 | 5.35 | 80.68 | 0
2 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13012 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Fatepur, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001554/2023-2024 | 4003227345 | 21/09/2023 | 20/12/2023 | W.B.S.E.D.C.LTD | 5.69 | 5.69 | 100 | 100
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13012 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Fatepur, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001553/2023-2024 | 4003227134 | 21/09/2023 | 20/12/2023 | W.B.S.E.D.C.LTD | 3.84 | 3.84 | 100 | 100
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13012 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 1218/RD/PHE | 02/05/2023 | 02/05/2023 | Resource Division | 97.41 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13012 | New | Additional pipeline and other ancillary works at Fatepur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000462/2024-2025 | 3780/RD/PHE | 19/12/2024 | 02/02/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.77 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13012 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Fatepur ,Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02567/2023-2024 | BP-2023-24-464 | 17/01/2024 | 17/01/2024 | W.B.S.E.D.C.LTD | 5.96 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13012 | New | Implementation of FATEPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000305/2022-2023 | 554/RD/PHE | 23/02/2023 | 31/08/2024 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 484.38 | 113.68 | 23.47 | 60
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13012 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under FATEPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000491/2023-2024 | 607/RD/PHE | 05/03/2024 | 18/07/2024 | M/S ARVI CONSTRUCTION | 22.58 | 0 | 0 | 60
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13012 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Fatepur Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000301/2025-2026 | 1950/RD/PHE | 01/07/2025 | 28/12/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.35 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13012 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head work site at T/W no. I of Fatepur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015104) | Assistant Engineer - I | Junior Engineer-02 | ORD/000531/2023-2024 | 2497/MLMD | 04/08/2023 | 26/03/2025 | ANIMA ENTERPRISE | 29.56 | 25.72 | 86.99 | 100
Total | [13 empty] | 731.17 | 154.27 | 21.1