## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Preparation & Submission of DPR for proposed Kochra Piped Water Supply Scheme under Karandighi Development Block. | Assistant Engineer RWS SD |  | ORD/000801/2021-2022 | 618/RD/PHE | 16/03/2022 | 15/04/2022 | ECO CARE | 5.16 | 4.16 | 80.69 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Implementation of KACHARA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000219/2022-2023 | 97/RD/PHE | 19/01/2023 | 01/01/2027 | SANYAL ENTERPRISE | 370.28 | 85.07 | 22.98 | 65
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Laying of Pipe line at KACHARA Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000036/2023-2024 | 1535/RD/PHE | 24/05/2023 | 08/07/2023 | M/S P.S. ENTERPRISE | 14.82 | 14.08 | 94.95 | 95
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Kachara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015107) | Assistant Engineer - I | Junior Engineer-02 | ORD/000672/2023-2024 | 2751/MLMD | 14/08/2023 | 08/02/2029 | DAS CONSTRUCTION | 32.67 | 23.27 | 71.22 | 71
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Kachara PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001943/2023-2024 | 4003220425 | 19/09/2023 | 18/12/2023 | W.B.S.E.D.C.LTD | 4.49 | 4.49 | 100 | 100
6 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Kachara PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001944/2023-2024 | 4003220426 | 08/09/2023 | 07/12/2023 | W.B.S.E.D.C.LTD | 5.57 | 5.57 | 100 | 100
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Material Requisition To Resource Division |  |  | RTOR000101/2022-2023 | 582/RD/PHE | 24/02/2023 | 24/02/2023 | Resource Division | 97.41 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000626/2023-2024 | 472/RD/PHE | 28/02/2024 | 28/06/2024 | PRITAM SARKAR | 1.6 | 0.4 | 24.95 | 0
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Kochra PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000450/2024-2025 | 3762/RD/PHED | 18/12/2024 | 01/02/2025 | UTTAM SAHA | 14.05 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KACHARA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000488/2023-2024 | 604/RD/PHE | 05/03/2024 | 25/09/2025 | BIMAL KUMAR SINHA | 22.57 | 0 | 0 | 65
11 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Additional quotation for HT cable at KACHARA PH-II under Karandighi ccc under Uttar Dinajpur. |  |  | BILL/03568/2023-2024 | BP-2023-24-583 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 6.99 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS |  |  | BILL/01220/2023-2024 | BP-2024-25-26 | 24/04/2024 | 24/04/2024 | EXECUTIVE ENGINEER PWD ROADS | 3.85 | 0 | 0 | 0
13 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Additional quotation for HT cable at KACHARA PH-I under Karandighi ccc under Uttar Dinajpur. |  |  | BILL/03567/2023-2024 | BP-2023-24-584 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 2.1 | 0 | 0 | 0
14 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kachra Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000411/2025-2026 | 2510/RD/PHE | 12/09/2025 | 11/03/2026 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 29.58 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 | New | Work Order for hiring charges of vehicle with fuel, hired for site works for RWS Raiganj Sub-Division under Raiganj Division, P.H.E. Dte. for the period from 17.09.2024 to 20.09.2024. |  |  | BILL/00696/2024-2025 | BP-2024-25-419 | 27/03/2025 | 27/03/2025 | M/S SARKAR ENTERPRISE SILIGURI | 0.09 | 0 | 0 | 0
Total | [13 empty] | 611.24 | 137.04 | 22.42