## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 | New | Laying Pipe line at MANKAUR Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD |  | ORD/000038/2023-2024 | 1537/RD/PHE | 24/05/2023 | 08/07/2023 | M/S P.S. ENTERPRISE | 15.39 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 | New | Preparation and Submission of DPR for proposed Mankaur Piped Water Supply Scheme under Karandighi Block. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000806/2021-2022 | 611/RD/PHED | 15/03/2022 | 14/04/2022 | M/S SOBHA & CO. | 4.4 | 4.4 | 100 | 0
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Mankaur ,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000638/2023-2024 | 4003196602 | 20/07/2023 | 18/10/2023 | W.B.S.E.D.C.LTD | 5.64 | 5.64 | 100 | 100
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Mankaur ,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000639/2023-2024 | 4003196598 | 20/07/2023 | 18/10/2023 | W.B.S.E.D.C.LTD | 8.66 | 8.66 | 100 | 100
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 | New | Material Requisition To Resource Division |  |  | RTOR000084/2022-2023 | 585/RD/PHE | 24/02/2023 | 24/02/2023 | Resource Division | 46.32 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head workite at T/W no. I of Mankaur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015108) | Assistant Engineer - I | Junior Engineer-02 | ORD/000523/2023-2024 | 2519/MLMD | 04/08/2023 | 19/06/2026 | PABITRA MANDAL | 25.32 | 21.74 | 85.84 | 86
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 | New | Implementation of MANKAUR andit's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000222/2022-2023 | 113/RD/PHE | 20/01/2023 | 04/04/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 379.57 | 139.92 | 36.86 | 60
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MANKAUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000531/2023-2024 | 599/RD/PHE | 05/03/2024 | 28/02/2025 | M/S CHOUDHURY CONSTRUCTION | 11.29 | 0 | 0 | 75
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MANKAUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000532/2023-2024 | 600/RD/PHE | 05/03/2024 | 28/02/2025 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 11.29 | 0 | 0 | 80
10 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 | New | Trial Run For Mankaur PWSS under Karandighi Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000719/2024-2025 | 551/RD/PHE | 12/02/2025 | 13/05/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Mankaur Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000327/2025-2026 | 2482/RD/PHE | 12/09/2025 | 11/03/2026 | BHOLA PAUL | 29.56 | 0 | 0 | 0
Total | [13 empty] | 538.31 | 180.36 | 33.5