## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Deona Piped Water Supply Scheme under Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/13020 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 2393/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.48 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Deona Piped Water Supply Scheme under Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/13020 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Deona Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000148/2022-2023 | 1926/RD/PHE | 28/10/2022 | 12/12/2022 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 32.87 | 0 | 0 | 15
3 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Deona Piped Water Supply Scheme under Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/13020 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Deona, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02498/2023-2024 | BP-2023-24-434 | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 4.41 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Deona Piped Water Supply Scheme under Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/13020 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Deona Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015282) | Assistant Engineer - I | Junior Engineer-02 | ORD/000487/2023-2024 | 2492/MLMD | 04/08/2023 | 26/03/2025 | SARADA MAA CONSTRUCTION. | 10.87 | 0 | 0 | 100
Total | [13 empty] | 50.63 | 0 | 0