## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 2263/RD/PHE | 23/12/2022 | 23/12/2022 | Resource Division | 116.35 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Construction of Over Head Reservoir(Capacity-700 Cum) of RAMGANJ(Zone-I) Pipe Water Supply Scheme in connection with Augmentation at Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000377/2022-2023 | 732/RD/PHE | 15/03/2023 | 14/03/2024 | SOVAN KUMAR ROY | 231.74 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | FHTC (Functional Household Tap Connection) for Ramganj Zone-I Water Supply Scheme [Augmentation Scheme] in Islampur Block Of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000403/2022-2023 | 758/RD/PHE | 17/03/2023 | 13/09/2023 | PRASANTA DUTTA | 123.24 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Repairing for 2nd Pump House & Construction of Toilet at Ramganj Zone-I in connection with Augmentation of Ramganj (Zone-I) PWSS under Islampur Sub-Division under Raiganj Division, PHE Dte.. | Assistant Engineer ISD |  | ORD/000108/2023-2024 | 2053/RD/PHE | 19/07/2023 | 02/09/2023 | MAA SHEETALA ENTERPRISE | 3.12 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Supply, installation & commissioning of electro-mechanical components at T/W no. I of Augmentation of Ramganj (Zone- I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011646) | Assistant Engineer - I | Junior Engineer-02 | ORD/000331/2023-2024 | 2333/MLMD | 26/07/2023 | 24/10/2023 | DEB CONSTRUCTION. | 12.27 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Ramganj (Zone- I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011646) | Assistant Engineer - I |  | ORD/000731/2023-2024 | 2695/MLMD | 11/08/2023 | 07/11/2028 | PABITRA MANDAL | 10.51 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Construction of Pump House at Head Work site (5.40mx3.60m) of Ramganj Zone-I Piped Water Supply Scheme in connection with Augmentation of Ramganj Zone-I PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000043/2023-2024 | 1542/RD/PHE | 24/05/2023 | 23/07/2023 | M/S ANTARA | 5.32 | 0 | 0 | 100
8 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Quotation for new service connection at RAMGANJ ZONE-I, PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/03774/2023-2024 | BP-2024-25-48 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 6.88 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Augmentation of RAMGANJ(Zone-I)Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000174/2022-2023 | 2119/RD/PHE | 02/12/2022 | 31/03/2025 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 324.17 | 0 | 0 | 30
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Construction of Pump House at 3rd Tube Well site (5.40mx3.60m) of Ramganj Zone-I Piped Water Supply Scheme in connection with Augmentation of Ramganj Zone -I PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000042/2023-2024 | 1541/RD/PHE | 24/05/2023 | 21/11/2024 | M/S ANTARA | 5.32 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. II & III of Augmentation of Ramganj (Zone- I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011646) | Assistant Engineer - I | Junior Engineer-02 | ORD/000332/2023-2024 | 2334/MLMD | 26/07/2023 | 12/11/2025 | MANIK CHANDRA SAHA. | 24.71 | 0 | 0 | 94
12 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
13 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Construction Of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site in connection with Augmentation Of Ramganj Zone-I PWSS at Chopra Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000336/2024-2025 | 3292/RD/PHE | 20/11/2024 | 04/01/2025 | MAA SHEETALA ENTERPRISE | 27.18 | 0 | 0 | 0
14 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 05/10/2024 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
15 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/13115 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Ramganj Zone-I Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 135 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000357/2025-2026 | 2503/RD/PHE | 12/09/2025 | 11/03/2026 | JAL PRAVAHIKA PRIVATE LIMITED | 47.78 | 0 | 0 | 0
Total | [13 empty] | 948.19 | 0 | 0