## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | DAKSHIN RAMPUR Piped Water Supply Scheme | SM/13232 | New | Material Requisition To Resource Division |  |  | RTOR000148/2022-2023 | 849/RD/PHE | 24/03/2023 | 24/03/2023 | Resource Division | 28.8 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | DAKSHIN RAMPUR Piped Water Supply Scheme | SM/13232 | New | Quotation for new service connection at Dakshin Rampur PH-I (Kanki ccc) in the district of Uttar Dinajpur. |  |  | BILL/03672/2023-2024 | BP-2023-24-655 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 6.23 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | DAKSHIN RAMPUR Piped Water Supply Scheme | SM/13232 | New | Quotation for new service connection at Dakshin Rampur PH-II (Kanki ccc) in the district of Uttar Dinajpur. |  |  | BILL/03673/2023-2024 | BP-2023-24-656 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 5.03 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | DAKSHIN RAMPUR Piped Water Supply Scheme | SM/13232 | New | Additional pipeline, Pathway, Land development and other ancillary works at Dakshin Rampur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division, P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000368/2025-2026 | 2268/RD/PHE | 07/08/2025 | 05/12/2025 | M/S PINKI CONSTRUCTION | 37.22 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | DAKSHIN RAMPUR Piped Water Supply Scheme | SM/13232 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 29/11/2025 | M/S GHOSH AND CO. | 12931.07 | 313.42 | 2.42 | 35
6 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | DAKSHIN RAMPUR Piped Water Supply Scheme | SM/13232 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dakshin Rampur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015519) | Assistant Engineer - I | Junior Engineer-02 | ORD/001809/2023-2024 | 3696/MLMD | 29/11/2023 | 27/01/2026 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 27.49 | 17.26 | 62.78 | 74
7 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | DAKSHIN RAMPUR Piped Water Supply Scheme | SM/13232 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshin Rampur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000318/2025-2026 | 1987/RD/PHE | 04/07/2025 | 31/12/2025 | AJIT PRAMANIK | 30.93 | 0 | 0 | 0
Total | [13 empty] | 13066.78 | 330.68 | 2.53