## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | BELAN Piped Water Supply Scheme | SM/13233 | New | Material Requisition To Resource Division |  |  | RTOR000180/2022-2023 | 981/RD/PHE | 30/03/2023 | 30/03/2023 | Resource Division | 50.16 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | BELAN Piped Water Supply Scheme | SM/13233 | New | Additional pipeline and other ancillary works at Belan piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000398/2025-2026 | 2337/RD/PHE | 22/08/2025 | 06/10/2025 | MILAN GHOSH | 45.48 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | BELAN Piped Water Supply Scheme | SM/13233 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Belan Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015468) | Assistant Engineer - I | Junior Engineer-02 | ORD/000408/2023-2024 | 2463/MLMD | 04/08/2023 | 29/09/2025 | JAL PRAVAHIKA PVT. LTD. | 28.11 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | BELAN Piped Water Supply Scheme | SM/13233 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 29/11/2025 | M/S GHOSH AND CO. | 12931.07 | 202.31 | 1.56 | 35
Total | [13 empty] | 13054.82 | 202.31 | 1.55