## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | BALDIABASA Piped Water Supply Scheme | SM/13234 | New | Material Requisition To Resource Division |  |  | RTOR000154/2022-2023 | 890/RD/PHE | 27/03/2023 | 27/03/2023 | Resource Division | 16.66 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | BALDIABASA Piped Water Supply Scheme | SM/13234 | New | Quotation for new service connection at BALDIABASA PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/13234) |  |  | BILL/01093/2024-2025 | BP-2024-25-272 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 16.82 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | BALDIABASA Piped Water Supply Scheme | SM/13234 | New | Quotation for new service connection at BALDIABASA PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/13234) |  |  | BILL/01094/2024-2025 | BP-2024-25-273 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 3.26 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | BALDIABASA Piped Water Supply Scheme | SM/13234 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Baldiabasa Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015377) | Assistant Engineer - I | Junior Engineer-02 | ORD/000406/2023-2024 | 2462/MLMD | 04/08/2023 | 27/05/2026 | JAL PRAVAHIKA PVT. LTD. | 25.49 | 0 | 0 | 81
5 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | BALDIABASA Piped Water Supply Scheme | SM/13234 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 26/08/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 150.02 | 1.16 | 35
Total | [13 empty] | 12993.29 | 150.02 | 1.15