## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | KABUTARKHOPI Piped Water Supply Scheme | SM/13235 | New | Material Requisition To Resource Division |  |  | RTOR000169/2022-2023 | 971/RD/PHE | 29/03/2023 | 29/03/2023 | Resource Division | 31.69 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | KABUTARKHOPI Piped Water Supply Scheme | SM/13235 | New | Quotation for new service connection at Kabutarkhopi PH-I (Kanki ccc) in the district of Uttar Dinajpur. |  |  | BILL/03674/2023-2024 | BP-2023-24-657 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 6.8 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | KABUTARKHOPI Piped Water Supply Scheme | SM/13235 | New | Quotation for new service connection at Kabutarkhopi PH-II (Kanki ccc) in the district of Uttar Dinajpur. |  |  | BILL/03675/2023-2024 | BP-2023-24-658 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 14.37 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | KABUTARKHOPI Piped Water Supply Scheme | SM/13235 | New | Additional pipeline and other ancillary works at Kabutar Khopi piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000400/2025-2026 | 2340/RD/PHE | 22/08/2025 | 06/10/2025 | MILAN GHOSH | 34.47 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | KABUTARKHOPI Piped Water Supply Scheme | SM/13235 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 29/11/2025 | M/S GHOSH AND CO. | 12931.07 | 251.31 | 1.94 | 35
6 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | KABUTARKHOPI Piped Water Supply Scheme | SM/13235 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kabutarkhopi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000452/2024-2025 | 3755/MLMD | 27/11/2024 | 22/11/2025 | DAS CONSTRUCTION | 26.2 | 0 | 0 | 81
Total | [13 empty] | 13044.6 | 251.31 | 1.93