## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. | SM/13456 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1198/RD/PHE | 28/04/2023 | 28/04/2023 | Resource Division | 35.74 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. | SM/13456 | New | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 23.08.2024 & 28.08.2024. |  |  | BILL/00387/2024-2025 | BP-2024-25-221 | 04/10/2024 | 04/10/2024 | SAHA CONSTRUCTION | 0.08 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. | SM/13456 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Agoi, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02492/2023-2024 | BP-2023-24-428 | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 4.95 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. | SM/13456 | New | Quotation for new service connection at AGOI PH-I (Goalpokher CCC) in the district of Uttar Dinajpur. |  |  | BILL/03634/2023-2024 | BP-2023-24-618 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 5.2 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. | SM/13456 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Agoi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015320) | Assistant Engineer - I | Junior Engineer-02 | ORD/000399/2023-2024 | 2457/MLMD | 04/08/2023 | 21/11/2025 | M/S D.G.B. ENTERPRISE. | 27.27 | 0 | 0 | 86
6 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. | SM/13456 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 6530.5 | 0 | 0 | 38
7 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. | SM/13456 | New | Providing FHTC in connection with Agoi Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000026/2025-2026 | 1181/RD/PHE | 23/04/2025 | 23/05/2025 | ANILA CONSTRUCTION | 5.06 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. | SM/13456 | New | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at AGOI PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000020/2025-2026 | 1204/RD/PHE | 25/04/2025 | 09/06/2025 | M/S PINKI CONSTRUCTION | 63.3 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. | SM/13456 | New | Providing FHTC in connection with Agoi Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000025/2025-2026 | 1182/RD/PHE | 23/04/2025 | 23/05/2025 | M/S SARKAR ENTERPRISE | 5.06 | 0 | 0 | 0
Total | [13 empty] | 6677.14 | 0 | 0