## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13502 | New | Material Requisition To Resource Division |  |  | RTOR000176/2022-2023 | 977/RD/PHE | 30/03/2023 | 30/03/2023 | Resource Division | 34.86 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13502 | New | Quotation for new service connection at MALIGAON PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(SM/13502) |  |  | BILL/00739/2024-2025 | BP-2024-25-239 | 29/05/2024 | 29/05/2024 | W.B.S.E.D.C.LTD | 12.83 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13502 | New | Additional pipeline, Pathway, Land development and other ancillary works at MALIGAON piped water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000395/2025-2026 | 2292/RD/PHE | 14/08/2025 | 12/12/2025 | M/S RADHASWAMI ENTERPRISE | 58.95 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13502 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Maligaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015800) | Assistant Engineer - I | Junior Engineer-02 | ORD/000524/2023-2024 | 2520/MLMD | 04/08/2023 | 27/01/2026 | M/S. KUNDU CONSTRACTION | 27.47 | 18.48 | 67.25 | 80
5 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13502 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 29/11/2025 | M/S GHOSH AND CO. | 12931.07 | 251.78 | 1.95 | 35
Total | [13 empty] | 13065.18 | 270.26 | 2.07