## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13503 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Tarapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015620) | Assistant Engineer - I | Junior Engineer-02 | ORD/000546/2023-2024 | 2536/MLMD | 04/08/2023 | 29/10/2025 | MANIK CHANDRA SAHA. | 26.44 | 19.06 | 72.09 | 72
2 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13503 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 26/08/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 220.76 | 1.71 | 35
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13503 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1044/RD/PHE | 05/04/2023 | 05/04/2023 | Resource Division | 29.31 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13503 | New | Quotation for Tarapur PH-II pwss (Kanki CCC). |  |  | BILL/03485/2023-2024 | BP-2023-24-518 | 08/02/2024 | 08/02/2024 | W.B.S.E.D.C.LTD | 7.72 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13503 | New | Quotation for new service connection at TARAPUR PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00212/2024-2025 | BP-2024-25-88 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 6.92 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13503 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Tarapur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000293/2025-2026 | 1826/RD/PHE | 25/06/2025 | 22/12/2025 | AJIT PRAMANIK | 29.59 | 0 | 0 | 0
Total | [13 empty] | 13031.05 | 239.82 | 1.84