## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | Implementation of PANDITPOTA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000307/2022-2023 | 569/RD/PHE | 23/02/2023 | 27/12/2025 | SANYAL ENTERPRISE | 320.79 | 92.15 | 28.73 | 81
2 | UTTAR DINAJPUR | Islampur | Malda Mechanical | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Panditpota Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015533) | Assistant Engineer - I | Junior Engineer-02 | ORD/000534/2023-2024 | 2528/MLMD | 04/08/2023 | 26/06/2026 | M/S S. S. ENTERPRISE | 28.05 | 19.66 | 70.1 | 84
3 | UTTAR DINAJPUR | Islampur | Malda Mechanical | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of PANDITPOTA, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000794/2023-2024 | 4003215071 | 23/08/2023 | 21/11/2023 | W.B.S.E.D.C.LTD | 8.43 | 8.43 | 100 | 100
4 | UTTAR DINAJPUR | Islampur | Malda Mechanical | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of PANDITPOTA, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001513/2023-2024 | 4003229632 | 13/09/2023 | 12/12/2023 | W.B.S.E.D.C.LTD | 4.25 | 4.25 | 100 | 100
5 | UTTAR DINAJPUR | Islampur | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | Material Requisition To Resource Division |  |  | RTOR000106/2022-2023 | 599/RD/PHE | 27/02/2023 | 27/02/2023 | Resource Division | 24.54 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of Islampur- Amaljhari- Sonamoti Road under Uttar Dinajpur division, PWD. |  |  | BILL/00506/2023-2024 | BILL/00506/2023 | 30/09/2023 | 30/09/2023 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 7.97 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | Laying of Additional Pipeline ,FHTC with Land development and Path way for PANDITPOTA Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000417/2024-2025 | 3581/RD/PHE | 05/12/2024 | 19/01/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 65.94 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PANDITPOTA PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000052/2024-2025 | 1711/RD/PHE | 10/06/2024 | 07/03/2025 | BHAGYA LAXMI ENTERPRISE | 22.59 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Islampur | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | Construction Of Single Row 1200 Mm Dia Np3 Hume Pipe Culvert In Front Of Panditpota Head Works Site For Approach Road Under Raiganj Division, Phe Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000414/2024-2025 | 3578/RD/PHE | 05/12/2024 | 20/12/2024 | UTTAM SAHA | 3.13 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Islampur | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0.33 | 6.61 | 100
11 | UTTAR DINAJPUR | Islampur | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | Providing FHTC in connection with Panditpota Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000509/2024-2025 | 54/RD/PHE | 03/01/2025 | 17/02/2025 | SANYAL ENTERPRISE | 10.39 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Islampur | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
13 | UTTAR DINAJPUR | Islampur | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Panditpota Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000296/2025-2026 | 1924/RD/PHE | 30/06/2025 | 27/12/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 18.74 | 0 | 0 | 0
Total | [13 empty] | 524.82 | 124.83 | 23.79