## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13550 | New | Material Requisition To Resource Division |  |  | RTOR000181/2022-2023 | 984/RD/PHE | 30/03/2023 | 30/03/2023 | Resource Division | 30.7 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13550 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Puar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015848) | Assistant Engineer - I | Junior Engineer-02 | ORD/000527/2023-2024 | 2524/MLMD | 04/08/2023 | 21/03/2026 | MERCURY ENGINEERING COMPANY. | 29.75 | 22.42 | 75.38 | 75
3 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13550 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte | Assistant Engineer - I | Junior Engineer-04 | ORD/000168/2024-2025 | 1670/MLMD | 25/06/2024 | 26/08/2024 | RAMCHANDRA BASAK | 0.78 | 0.77 | 99.14 | 100
4 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13550 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 26/08/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 286.45 | 2.22 | 35
Total | [13 empty] | 12992.29 | 309.65 | 2.38