## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Malda Mechanical | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13717 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of DHANTOLA, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000984/2023-2024 | 4003229554 | 13/09/2023 | 12/12/2023 | W.B.S.E.D.C.LTD | 4.14 | 0 | 0 | 100
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13717 | New | Material Requisition To Resource Division |  |  | RTOR000116/2022-2023 | 603/RD/PHE | 27/02/2023 | 27/02/2023 | Resource Division | 109 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Islampur | Malda Mechanical | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13717 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Dhantola Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014170) | Assistant Engineer - I | Junior Engineer-02 | ORD/000493/2023-2024 | 2494/MLMD | 04/08/2023 | 26/02/2026 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD.. | 42.27 | 0 | 0 | 58
4 | UTTAR DINAJPUR | Islampur | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13717 | New | Construction of Boundary Wall with Gate at Head Work Site, 2nd & 3rd Tube-Well Site under DHANTOLA Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000456/2023-2024 | 564/RD/PHE | 05/03/2024 | 01/09/2024 | M/S CAMELLIA CONSTRUCTION AND CO. | 27.65 | 0 | 0 | 100
5 | UTTAR DINAJPUR | Islampur | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13717 | New | Implementation of DHANTALA and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line,Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd & 3rdTube Well.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000331/2022-2023 | 674/RD/PHE | 06/03/2023 | 01/04/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 840.35 | 0 | 0 | 6
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13717 | New | Construction Of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Dhantola PWSS at Islampur Block under Raiganj Division, PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000166/2024-2025 | 2894/RD/PHE | 25/09/2024 | 15/10/2024 | SHANKAR SAHA | 4.31 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13717 | New | Providing FHTC in connection with Dhantaola Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000507/2024-2025 | 52/RD/PHE | 03/01/2025 | 17/02/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 8.23 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13717 | New | Laying of Additional pipeline with other ancillary works at different mouzas of DHANTALA PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000372/2024-2025 | 3491/RD/PHE | 02/12/2024 | 16/01/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 55.01 | 0 | 0 | 0
Total | [13 empty] | 1090.96 | 0 | 0