## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra | Raiganj Division | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13738 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 1476/RD/PHE | 16/05/2023 | 16/05/2023 | Resource Division | 43.66 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Chopra | Malda Mechanical | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13738 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jiakhori Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015618) | Assistant Engineer - I | Junior Engineer-02 | ORD/000555/2023-2024 | 2506/MLMD | 04/08/2023 | 19/07/2026 | MAA BHABOTARINE ENTERPRISE. | 28.31 | 20.99 | 74.16 | 74
3 | UTTAR DINAJPUR | Chopra | Malda Mechanical | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13738 | New | Quotation for new service connection at JIAKHORI PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/13738) |  |  | BILL/01084/2024-2025 | BP-2024-25-301 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 3.98 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Chopra | Raiganj Division | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13738 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 7213.93 | 138.6 | 1.92 | 30
5 | UTTAR DINAJPUR | Chopra | Raiganj Division | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13738 | New | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at JIAKHORI PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000032/2025-2026 | 1211/RD/PHE | 25/04/2025 | 09/06/2025 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 69.49 | 0 | 0 | 0
Total | [13 empty] | 7359.36 | 159.59 | 2.17