## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13739 | New | Material Requisition To Resource Division |  |  | RTOR000107/2022-2023 | 598/RD/PHE | 27/02/2023 | 27/02/2023 | Resource Division | 43.88 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13739 | New | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of Islampur- Amaljhari- Sonamoti Road under Uttar Dinajpur division, PWD. |  |  | BILL/00506/2023-2024 | BILL/00506/2023 | 30/09/2023 | 30/09/2023 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 7.97 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13739 | New | Implementation of KHABARGAON and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000308/2022-2023 | 567/RD/PHE | 23/02/2023 | 01/04/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 496.73 | 141.72 | 28.53 | 50
4 | UTTAR DINAJPUR | Islampur | Malda Mechanical | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13739 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Khabargaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015710) | Assistant Engineer - I | Junior Engineer-02 | ORD/000514/2023-2024 | 2511/MLMD | 04/08/2023 | 26/02/2026 | SUBHAS CHANDRA KESHORI | 28.32 | 21 | 74.16 | 75
5 | UTTAR DINAJPUR | Islampur | Raiganj Division | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13739 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KHABARGAON PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000492/2023-2024 | 608/RD/PHE | 05/03/2024 | 19/04/2024 | DUTTA BUILDERS | 22.51 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Malda Mechanical | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13739 | New | Quotation for new service connection at KHABARGAON PH-II (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/13739) |  |  | BILL/01092/2024-2025 | BP-2024-25-271 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 5.42 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13739 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Khabargaon Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000300/2025-2026 | 1949/RD/PHE | 01/07/2025 | 28/12/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.36 | 0 | 0 | 0
Total | [13 empty] | 637.19 | 162.72 | 25.54