## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Malda Mechanical | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of JAGATAGAON, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000796/2023-2024 | 4003215033 | 23/08/2023 | 21/11/2023 | W.B.S.E.D.C.LTD | 5.01 | 5.01 | 100 | 100
2 | UTTAR DINAJPUR | Islampur | Malda Mechanical | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of JAGATAGAON, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000795/2023-2024 | 4003215012 | 23/08/2023 | 21/11/2023 | W.B.S.E.D.C.LTD | 8.89 | 8.89 | 100 | 100
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | Material Requisition To Resource Division |  |  | RTOR000098/2022-2023 | 581/RD/PHE | 24/02/2023 | 24/02/2023 | Resource Division | 75.77 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Islampur | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | Protection and Restoration work of damaged flank caused by excavation for water supply project of PHE of Matikunda- Moragoti Road under uttar dinajpur division, PWD. |  |  | BILL/00505/2023-2024 | BP-2023-24-143 | 30/09/2023 | 30/09/2023 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 9.23 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Malda Mechanical | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I, II & III and making compound lighting arrangement at T/W no. I of Jagatgaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013510) | Assistant Engineer - I | Junior Engineer-02 | ORD/000413/2023-2024 | 2443/MLMD | 04/08/2023 | 29/09/2025 | GHOSH BROTHERS... | 39.57 | 30.52 | 77.12 | 77
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | Construction of concrete pathway with earth filling at Head Work Site Pump House & 2nd TW Site Pump House for JAGTAGAON Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000351/2024-2025 | 3304/RD/PHE | 20/11/2024 | 20/12/2024 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 9.63 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | Implementation of JAGATGAON and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000271/2022-2023 | 289/RD/PHE | 01/02/2023 | 05/09/2025 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 910.72 | 586.58 | 64.41 | 60
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | Additional pipeline and other ancillary works at Jagtagaon piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000350/2024-2025 | 3303/RD/PHE | 20/11/2024 | 04/04/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 49.57 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Islampur | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | Construction of Boundary Wall with Gate at Head Work Site, 2nd & 3rd Tube-Well Site under JAGATAGAON Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000453/2023-2024 | 561/RD/PHE | 05/03/2024 | 28/02/2025 | M/S RATAN SARKAR & SON | 27.68 | 6.19 | 22.35 | 85
10 | UTTAR DINAJPUR | Islampur | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | Providing FHTC in connection with Jagtagaon Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000510/2024-2025 | 55/RD/PHE | 03/01/2025 | 17/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 5.98 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Islampur | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 05/10/2024 | SISIR KUMAR DUTTA | 4.8 | 0.73 | 15.14 | 0
12 | UTTAR DINAJPUR | Islampur | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 | New | Trial Run For Jagtagaon PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000718/2024-2025 | 550/RD/PHE | 12/02/2025 | 13/05/2025 | CHAPDUAR LABOUR CO- OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.87 | 0 | 0 | 0
Total | [13 empty] | 1147.73 | 637.91 | 55.58