## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 2178/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 55.82 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Atghara PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001879/2023-2024 | 4003202769 | 03/08/2023 | 01/11/2023 | W.B.S.E.D.C.LTD | 5.71 | 5.71 | 100 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.III of Atghara, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001877/2023-2024 | 4003202782 | 08/08/2023 | 06/11/2023 | W.B.S.E.D.C.LTD | 5.13 | 5.13 | 100 | 100
4 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Implementation of ATGHARA and it's adjoining mouzas Pipe Water Supply Scheme at Kaliyaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000272/2022-2023 | 290/RD/PHE | 01/02/2023 | 01/07/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 892 | 617.96 | 69.28 | 60
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Approach road with land development of headwork site & 2nd tubewell site and road restoration of Atghara PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000458/2024-2025 | 3776/RD/PHE | 19/12/2024 | 02/02/2025 | M/S P.S. ENTERPRISE | 12.46 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under ATGHARA Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000457/2023-2024 | 565/RD/PHE | 05/03/2024 | 17/08/2024 | M/S P.S. ENTERPRISE | 27.93 | 17.91 | 64.11 | 25
7 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of ATGHARA PWSS ,Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02583/2023-2024 | BP-2023-24-475 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 11.12 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Additional Quotation of TW-II of Ataghara water supply scheme in the district if Uttar Dinajpur. |  |  | BILL/01827/2024-2025 | BP-2024-25-457 | 23/08/2024 | 23/08/2024 | W.B.S.E.D.C.LTD | 6.67 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Requisition of fund regarding payment for permanent restoration of rural roads damaged due to laying of pipeline by PHE Dte. as on 24.09.2024 i.c.w L026-FATEPUR to PURBA SANKARPUR (Package No. WB15301: Under DLP), under coverage of Atghara PWSS (SM/13796) |  |  | BILL/00474/2024-2025 | BP-2024-25-275 | 08/10/2024 | 08/10/2024 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.98 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Additional Quotation charge at TW No- I of Ataghara, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03775/2023-2024 | BP-2024-25-17 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 1.04 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer HQ | Estimator | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 28/06/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0.78 | 16.34 | 100
12 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Ataghara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012590) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000608/2023-2024 | 2652/MLMD | 10/08/2023 | 26/07/2026 | SUBRATA SAHA | 37.17 | 32.69 | 87.95 | 92
13 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month(Period from 01.07.2023 to 30.06.2024). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000625/2023-2024 | 1722/RD/PHE | 28/06/2023 | 28/06/2024 | DEBASISH GHOSH | 4.8 | 1.18 | 24.6 | 0
14 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Trial Run For Atghara PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000682/2024-2025 | 528/RD/PHE | 12/02/2025 | 13/05/2025 | AJIT PRAMANIK | 0.88 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Atghara Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 100 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000259/2025-2026 | 1620/RD/PHE | 19/06/2025 | 16/12/2025 | AJIT PRAMANIK | 36.38 | 0 | 0 | 0
16 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Additional pipe line laying for Atghara Piped Water Supply Scheme due to revision of drawing at Kaliyaganj Block of Uttar Diunajpur District under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000133/2024-2025 | 2835/RD/PHE | 23/09/2024 | 22/12/2024 | M/S P.S. ENTERPRISE | 49.53 | 0 | 0 | 100
17 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Vehicle no.WB 59C 4762) having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office ofthe Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entireRaiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Estimator | ORD/000408/2024-2025 | 1981/RD/PHE | 29/06/2024 | 13/01/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 2.6 | 0.4 | 15.38 | 100
Total | [13 empty] | 1156.02 | 681.76 | 58.98