## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | PRATAPPUR PIPED WATER SUPPLY SCHEME | SM/14128 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1201/RD/PHE | 28/04/2023 | 28/04/2023 | Resource Division | 37.78 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | PRATAPPUR PIPED WATER SUPPLY SCHEME | SM/14128 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of PRATAPPUR, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02496/2023-2024 | BP-2023-24-432 | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 11.43 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | PRATAPPUR PIPED WATER SUPPLY SCHEME | SM/14128 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of PRATAPPUR, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02495/2023-2024 | BP-2023-24-431 | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 5.69 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | PRATAPPUR PIPED WATER SUPPLY SCHEME | SM/14128 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 6530.5 | 0 | 0 | 38
5 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | PRATAPPUR PIPED WATER SUPPLY SCHEME | SM/14128 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Pratappur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016739) | Assistant Engineer - I | Junior Engineer-02 | ORD/001804/2023-2024 | 3691/MLMD | 29/11/2023 | 27/12/2025 | MERCURY ENGINEERING COMPANY. | 27.51 | 0 | 0 | 85
6 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | PRATAPPUR PIPED WATER SUPPLY SCHEME | SM/14128 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pratappur Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000341/2025-2026 | 1803/RD/PHE | 24/06/2025 | 21/12/2025 | JAL PRAVAHIKA PRIVATE LIMITED | 29.55 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | PRATAPPUR PIPED WATER SUPPLY SCHEME | SM/14128 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at PRATAPPUR PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000270/2025-2026 | 2087/RD/PHE | 14/07/2025 | 10/01/2026 | ROY ENGINEERS. (PATNA) | 38.64 | 0 | 0 | 0
Total | [13 empty] | 6681.09 | 0 | 0