## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | FASHIA DIATION PIPED WATER SUPPLY SCHEME | SM/14129 | New | Material Requisition To Resource Division |  |  | RTOR000179/2022-2023 | 979/RD/PHE | 30/03/2023 | 30/03/2023 | Resource Division | 38.57 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | FASHIA DIATION PIPED WATER SUPPLY SCHEME | SM/14129 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Fashia Diation Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016516) | Assistant Engineer - I | Junior Engineer-02 | ORD/000409/2023-2024 | 2441/MLMD | 04/08/2023 | 26/02/2026 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD.. | 27.22 | 0 | 0 | 53
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | FASHIA DIATION PIPED WATER SUPPLY SCHEME | SM/14129 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 26/08/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
Total | [13 empty] | 12996.86 | 0 | 0