## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Providing functional house hold tap connection at Village-Amritkhanda of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000419/2022-2023 | 774/RD/PHE | 17/03/2023 | 16/05/2023 | M/S BHOWMIK CONSTRUCTION | 16 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Construction of OHR (Capacity-250Cum) of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur district under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000510/2022-2023 | 853/RD/PHE | 24/03/2023 | 24/12/2023 | DIPAK SAHA | 95.39 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Providing Functional House Hold Tap Connection at village- Bishahar of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000548/2022-2023 | 960/RD/PHE | 29/03/2023 | 28/05/2023 | DAS CONSTRUCTION COMPANY | 15.45 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Laying, Rising-Main of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000515/2022-2023 | 858/RD/PHE | 24/03/2023 | 23/05/2023 | M/S MANDAL ENTERPRISE TUMPASONU05@YAHOO.COM | 4.52 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Construction of Pump house and boundary wall at Head Work Site of Bishahar PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000487/2022-2023 | 826/RD/PHE | 22/03/2023 | 21/05/2023 | DISCOVERY CO. OPERATIVE LABOUR CONT AND CONST SOC. LTD. | 24.86 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Bishahar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018229) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000416/2023-2024 | 2468/MLMD | 04/08/2023 | 02/12/2023 | R. S. ENTERPRISE | 25.32 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 1679/RD/PHE | 19/06/2023 | 19/06/2023 | Resource Division | 39.44 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Kokra, 2.Bishahar, 3. Dhoabishua in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000290/2022-2023 | 539/RD/PHE | 22/02/2023 | 13/11/2024 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 12.39 | 15.57 | 65
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Laying Pipe line at Village-Bishahar of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000547/2022-2023 | 959/RD/PHE | 29/03/2023 | 28/05/2023 | MAA SHEETALA ENTERPRISE | 40.95 | 29.95 | 73.12 | 35
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Laying distribution of Pipe line of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000473/2022-2023 | 820/RD/PHE | 22/03/2023 | 06/05/2023 | M/S P.S. ENTERPRISE | 47.35 | 31.85 | 67.27 | 20
11 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Laying pipe line at Dakhshin Bishnupur of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000537/2022-2023 | 949/RD/PHED | 29/03/2023 | 28/05/2023 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 40.88 | 38.92 | 95.21 | 15
12 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Laying of pipe line at Village-Amritakhanda of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000409/2022-2023 | 764/RD/PHE | 17/03/2023 | 16/05/2023 | M/S PIONEER ENTERPRISE | 40.84 | 29.3 | 71.74 | 20
13 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Laying of Pipe Line at village-Birahimkhanda & Ital of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000520/2022-2023 | 874/RD/PHE | 27/03/2023 | 26/05/2023 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 41.03 | 29.21 | 71.21 | 20
14 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Bishahar, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03640/2023-2024 | BP-2023-24-624 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 3.74 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Providing functional House hold tap connection at village-Birhimkhanda & Ital of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000529/2022-2023 | 879/RD/PHE | 27/03/2023 | 31/03/2025 | SANDIP SARKAR | 15.22 | 0 | 0 | 15
16 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer HQ | Estimator | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 28/06/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
17 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Providing functional house hold tap connection at village-Dakhshin Bishnupur of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000100/2023-2024 | 2047/RD/PHE | 19/07/2023 | 01/04/2025 | SANDIP SARKAR | 16.32 | 0 | 0 | 0
18 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Vehicle no.WB 59C 4762) having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office ofthe Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entireRaiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Estimator | ORD/000408/2024-2025 | 1981/RD/PHE | 29/06/2024 | 13/01/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 2.6 | 0 | 0 | 100
19 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bishahar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000483/2024-2025 | 16/RD/PHE | 02/01/2025 | 16/02/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 24.95 | 0 | 0 | 0
20 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14144 | New | Construction of boundary wall and Pump house at 2nd tube-well of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000414/2022-2023 | 769/RD/PHE | 17/03/2023 | 07/09/2024 | DULAL DUTTA | 11.28 | 0 | 0 | 100
Total | [13 empty] | 590.53 | 171.63 | 29.06