## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14145 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Dakshin Goalpara, 2. Bhattagidighi, 3. Maharajpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000291/2022-2023 | 540/RD/PHE | 22/02/2023 | 13/11/2024 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 5.64 | 7.08 | 80
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14145 | New | Providing FHTC with laying distribution of pipe line at village Taherpur of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000404/2022-2023 | 759/RD/PHE | 16/03/2023 | 04/04/2025 | M/S JHA CONSTRUCTION | 91.73 | 0 | 0 | 50
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14145 | New | Construction of Boundary Wall and Pump House at 2nd Tube-Well with providing Functional House hold Tap Connection of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000475/2022-2023 | 821/RD/PHE | 22/03/2023 | 21/05/2023 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 39.84 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14145 | New | Implementation of DAKHSHIN GOALPARA andit's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ BLOCK of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000009/2023-2024 | 1271/RD/PHE | 08/05/2023 | 07/04/2025 | PRASANTA DUTTA | 206.31 | 0 | 0 | 50
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14145 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Dakshin Goalpara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018225) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000484/2023-2024 | 2490/MLMD | 04/08/2023 | 27/01/2026 | M/S TRILOCHAN CONSTRUCTION CO. | 25.28 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14145 | New | Laying distribution of pipe Line and Providing FHTC at Village Dakhin Goal Para of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000582/2022-2023 | 854/RD/PHE | 24/03/2023 | 22/04/2025 | M/S AMIT KUMAR GUPTA | 85.53 | 0 | 0 | 80
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14145 | New | Laying of pipe line at Naopara of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000455/2022-2023 | 815/RD/PHE | 22/03/2023 | 06/05/2023 | M/S P.S. ENTERPRISE | 50.51 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14145 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 1570/RD/PHE | 31/05/2023 | 31/05/2023 | Resource Division | 43.02 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14145 | New | pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dakshin Goalpara PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000485/2024-2025 | 18/RD/PHE | 02/01/2025 | 01/02/2025 | M/S JHA CONSTRUCTION | 18.16 | 0 | 0 | 0
Total | [13 empty] | 639.99 | 5.64 | 0.88