## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 0 | 0 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 2237/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 27.73 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehical No. WB60T 9215) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 17.10.2024 to 14.01.2025) | Assistant Engineer RSD |  | ORD/000409/2024-2025 | 3045/RD/PHE | 04/10/2024 | 02/01/2025 | ARNAB DUTTA | 1.2 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 | New | Construction Culvert with Hume Pipe Across PWD Borrow Pit for Making Accessible Road at Bahin Paharpur PWSS Head Work Site at Hemtabad Block under Raiganj Division, P.H.E. Dte., Raiganj, Uttar Dinajpur. |  | Junior Engineer, RSD | ORD/000120/2024-2025 | 3010/RD/PHE | 03/10/2024 | 02/11/2024 | BHOLA PAUL | 4.22 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.II of Bahin Paharpur, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02577/2023-2024 | BP-2023-24-469 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 3.49 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 | New | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS |  |  | BILL/01218/2023-2024 | BP-2024-25-25 | 24/04/2024 | 24/04/2024 | EXECUTIVE ENGINEER PWD ROADS | 14.43 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Bahin Paharpur, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02576/2023-2024 | BP-2023-24-468 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 5.12 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 | New | Implementation of BAHIN PAHARPUR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000314/2022-2023 | 563/RD/PHE | 23/02/2023 | 14/11/2025 | BHOLA PAUL | 305.86 | 0 | 0 | 53
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer HQ | Estimator | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 28/06/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
10 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite at T/W no. I of Bahin Paharpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017738) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000410/2023-2024 | 2464/MLMD | 04/08/2023 | 16/02/2025 | SUBHRA ENTERPRISE | 25.01 | 0 | 0 | 93
11 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bahin Paharpur PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000433/2024-2025 | 3746/RD/PHE | 18/12/2024 | 02/05/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 32.59 | 0 | 0 | 0
Total | [13 empty] | 487.5 | 0 | 0