## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14163 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite at T/W no. I of Bhattagidighi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018205) | Assistant Engineer - I | Junior Engineer-07 | ORD/000633/2023-2024 | 2734/MLMD | 14/08/2023 | 10/02/2024 | SHREE BISHNU CONSTRUCTION | 26.91 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14163 | New | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 578/RD/PHE | 24/02/2023 | 24/02/2023 | Resource Division | 47.07 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14163 | New | Implementation of BHATTAGIDIGHI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000322/2022-2023 | 559/RD/PHE | 23/02/2023 | 01/01/2026 | M/S LOKENATH CONSTRUCTION | 618.78 | 107.5 | 17.37 | 45
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14163 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Bhattagidighi, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03545/2023-2024 | BP-2023-24-572 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 5.69 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14163 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Bhattagidighi, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03638/2023-2024 | BP-2023-24-622 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 10.22 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14163 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Dakshin Goalpara, 2. Bhattagidighi, 3. Maharajpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000291/2022-2023 | 540/RD/PHE | 22/02/2023 | 13/11/2024 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 22.86 | 28.72 | 80
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14163 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer HQ | Estimator | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 28/06/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14163 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site , Tube well and Pump Houseroad restoration of Bhattadighi PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000469/2024-2025 | 02/RD/PHE | 02/01/2025 | 16/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 69.15 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14163 | New | Continuation Order for Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C, Vehicle No. WB 59D 1337) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Months (Period from 15.01.2025 to 14.07.2025). | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000810/2024-2025 | 299/RD/PHE | 15/01/2025 | 15/07/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 2.4 | 0 | 0 | 0
Total | [13 empty] | 864.62 | 130.36 | 15.08