## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Providing FHTC at village-Kamat of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000416/2022-2023 | 771/RD/PHE | 17/03/2023 | 16/05/2023 | PANDIT CONSTRUCTION PANDIT.RNJ@GMAIL.COM | 15.4 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Providing FHTC at village-Pargaon of ALIANAGAR Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000526/2022-2023 | 876/RD/PHE | 27/03/2023 | 26/05/2023 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 17.46 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1318/RD/PHE | 12/05/2023 | 12/05/2023 | Resource Division | 46.84 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Raniganj, 2. Alianagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000296/2022-2023 | 542/RD/PHE | 22/02/2023 | 11/11/2024 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 51.42 | 20.07 | 39.03 | 80
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Alianagar PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000453/2024-2025 | 3766/RD/PHED | 18/12/2024 | 01/02/2025 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 33.63 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. |  |  | BILL/00017/2024-2025 | BP-2024-25-11 | 08/04/2024 | 08/04/2024 | M/S DILWAR HOSAIN | 0.07 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. |  |  | BILL/00021/2024-2025 | BP-2024-25-15 | 08/04/2024 | 08/04/2024 | M/S DILWAR HOSAIN | 0.05 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. |  |  | BILL/00018/2024-2025 | BP-2024-25-12 | 08/04/2024 | 08/04/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. |  |  | BILL/00020/2024-2025 | BP-2024-25-14 | 08/04/2024 | 08/04/2024 | M/S DILWAR HOSAIN | 0.09 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. |  |  | BILL/00019/2024-2025 | BP-2024-25-13 | 08/04/2024 | 08/04/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Construction of boundary wall and Pump house at 2nd Tube-well site of Aliangar Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000411/2022-2023 | 766/RD/PHE | 17/03/2023 | 16/02/2025 | M/S UNIQUE 13 | 11.28 | 2.27 | 20.13 | 100
12 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Laying of pipe line at village-Kamat of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000406/2022-2023 | 761/RD/PHE | 17/03/2023 | 06/03/2025 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 49.21 | 0 | 0 | 35
13 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Laying of pipe line at village-Pargaon of ALIANAGAR Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000517/2022-2023 | 871/RD/PHE | 27/03/2023 | 19/03/2025 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 49.76 | 0 | 0 | 35
14 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Construction of OHR(Capacity-300Cum) of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000552/2022-2023 | 1020/RD/PHE | 31/03/2023 | 31/12/2023 | MS SANDHYA CONSTRUCTION | 96.8 | 0 | 0 | 35
15 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Providing FHTC of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000539/2022-2023 | 951/RD/PHE | 29/03/2023 | 18/11/2024 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 16.85 | 0 | 0 | 0
16 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Laying of pipe line at village-Alianagar of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000534/2022-2023 | 946/RD/PHE | 29/03/2023 | 17/04/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 45.14 | 0 | 0 | 37
17 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Laying distribution of pipe line of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000466/2022-2023 | 817/RD/PHE | 22/03/2023 | 24/02/2025 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 49.51 | 0 | 0 | 40
18 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Providing FHTC at village-Pargaon and Kamat of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000544/2022-2023 | 956/RD/PHE | 29/03/2023 | 17/01/2025 | M/S ARVI CONSTRUCTION | 18.26 | 0 | 0 | 0
19 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-04,Junior Engineer-07 | ORD/001790/2024-2025 | 4337/MLMD | 31/12/2024 | 28/02/2025 | NITAI PANDEY | 0.77 | 0 | 0 | 100
20 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Alianagar Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000331/2025-2026 | 2484/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 30.93 | 0 | 0 | 0
21 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Laying of Rising Main of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000512/2022-2023 | 855/RD/PHE | 24/03/2023 | 12/01/2025 | M/S DAS ENTERPRISE SUMAN974967@GMAIL.COM | 4.58 | 0 | 0 | 10
22 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Construction of boundary wall and Pump house at head work site of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000484/2022-2023 | 823/RD/PHE | 22/03/2023 | 11/09/2024 | GULJAN BEGAM | 24.87 | 23.16 | 93.12 | 100
23 | UTTAR DINAJPUR | Karandighi | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Approach Road for Head Work Site of Alianagar Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000126/2024-2025 | 3017/RD/PHE | 03/10/2024 | 23/10/2024 | TAPAN KUMAR ROY | 2.53 | 0 | 0 | 100
24 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Quotation for new service connection at ALIANAGAR PH-II (Karandighi ccc) in the district of Uttar Dinajpur (SM/14164). |  |  | BILL/02736/2024-2025 | BP-2024-25-612 | 09/01/2025 | 09/01/2025 | W.B.S.E.D.C.LTD | 4.91 | 0 | 0 | 0
25 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Quotation for new service connection at ALIANAGAR PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14164) |  |  | BILL/03206/2024-2025 | BP-2024-25-643 | 13/03/2025 | 13/03/2025 | W.B.S.E.D.C.LTD | 4.47 | 0 | 0 | 0
26 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14164 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Alianagar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017531) | Assistant Engineer - I | Junior Engineer-02 | ORD/000400/2023-2024 | 2458/MLMD | 04/08/2023 | 21/03/2026 | M/S D.G.B. ENTERPRISE. | 24.89 | 0 | 0 | 90
Total | [13 empty] | 599.92 | 45.5 | 7.58