## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Lahutara, 2. Hemenpur, 3. Basudebpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000295/2022-2023 | 541/RD/PHE | 22/02/2023 | 08/04/2023 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 61.71 | 19.36 | 31.38 | 60
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Providing FHTC at village- Dhangaon of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000417/2022-2023 | 772/RD/PHE | 17/03/2023 | 16/05/2023 | M/S P.S. ENTERPRISE | 17.95 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Laying pipe line at village- Dhangaon of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000407/2022-2023 | 762/RD/PHE | 17/03/2023 | 16/05/2023 | CHAITANYA SAMAL | 48.9 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Construction of Boundary Wall and Pump House at 2nd Tube-well site of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000412/2022-2023 | 767/RD/PHE | 17/03/2023 | 16/05/2023 | M/S UNIQUE 13 | 11.28 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Providing FHTC at village- Bhagdoarin of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000527/2022-2023 | 877/RD/PHE | 27/03/2023 | 26/05/2023 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 17.08 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Laying of Pipe line of village-Bhagdarin of LAHUTARA Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD ,Junior Engineer, RWS | ORD/000518/2022-2023 | 872/RD/PHE | 27/03/2023 | 24/11/2024 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 47.52 | 11.63 | 24.47 | 75
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Laying of Rising Main of LAHUTARA Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000513/2022-2023 | 856/RD/PHE | 24/03/2023 | 23/05/2023 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. LOKNATH.ITR@GMAIL.COM | 5.25 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Providing FHTC at village- Lahutara & Gurulbhasa of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000540/2022-2023 | 952/RD/PHE | 29/03/2023 | 28/05/2023 | JEET CONSTRUCTION UKILPARA CTNJIT38@GMAIL.COM | 19.57 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Construction of OHR(Capacity-300Cum) of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte.. | Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD ,Junior Engineer, RWS | ORD/000508/2022-2023 | 851/RD/PHE | 24/03/2023 | 02/03/2025 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 96.67 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Laying distribution of pipe line of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD ,Junior Engineer, RWS | ORD/000469/2022-2023 | 818/RD/PHE | 22/03/2023 | 21/03/2025 | BHOWMICK ENTERPRISE | 50.31 | 42.92 | 85.31 | 70
11 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Providing FHTC at village-Lahutara of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD ,Junior Engineer, RWS | ORD/000545/2022-2023 | 957/RD/PHE | 29/03/2023 | 22/07/2024 | RURAL DEVELOPMENT CO-OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 16.29 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Laying of pipe line at village -Lahutara & Gurul Bhasa of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000535/2022-2023 | 947/RD/PHED | 29/03/2023 | 28/05/2023 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 48.48 | 0 | 0 | 0
13 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer HQ | Estimator | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 28/06/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
14 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Lahutara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017508) | Assistant Engineer - I | Junior Engineer-02 | ORD/000520/2023-2024 | 2516/MLMD | 04/08/2023 | 26/06/2026 | TARUN KUMAR DEY | 25.08 | 19.24 | 76.73 | 77
15 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Construction of Boundary Wall and Pump House at head work site of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD ,Junior Engineer, RWS | ORD/000485/2022-2023 | 824/RD/PHE | 22/03/2023 | 08/09/2025 | RAKSHIT TRADERS | 24.85 | 0 | 0 | 100
16 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1321/RD/PHE | 12/05/2023 | 12/05/2023 | Resource Division | 44.41 | 0 | 0 | 0
17 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Vehicle no.WB 59C 4762) having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office ofthe Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entireRaiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Estimator | ORD/000408/2024-2025 | 1981/RD/PHE | 29/06/2024 | 13/01/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 2.6 | 0.4 | 15.38 | 100
18 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Laying of Additional pipeline with other ancillary works at different mouzas of LAHUTARA PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000379/2024-2025 | 3498/RD/PHE | 02/12/2024 | 29/08/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 48.12 | 0 | 0 | 30
19 | UTTAR DINAJPUR | Karandighi | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for LAHUTARA Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000367/2024-2025 | 3486/RD/PHE | 02/12/2024 | 01/01/2025 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 16.66 | 0 | 0 | 0
20 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14165 | New | Quotation for new service connection at LAHUTARA PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/ 14165) |  |  | BILL/02084/2024-2025 | BP-2024-25-485 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 12.11 | 0 | 0 | 0
Total | [13 empty] | 619.64 | 93.54 | 15.1