## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14167 | New | Material Requisition To Resource Division |  |  | RTOR000159/2022-2023 | 902/RD/PHE | 28/03/2023 | 28/03/2023 | Resource Division | 60.85 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14167 | New | Quotation for new service connection at CHITAURA PH-I (Kanki ccc) in the district of Uttar Dinajpur. |  |  | BILL/03668/2023-2024 | BP-2023-24-651 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 9.23 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14167 | New | Quotation for new service connection at CHITAURA PH-I (Kanki ccc) in the district of Uttar Dinajpur. |  |  | BILL/03669/2023-2024 | BP-2023-24-652 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 8.8 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14167 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 29/11/2025 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
5 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14167 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chitaura Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016571) | Assistant Engineer - I | Junior Engineer-02 | ORD/001808/2023-2024 | 3695/MLMD | 29/11/2023 | 29/10/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 27.49 | 0 | 0 | 84
6 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14167 | New | Additional pipeline and other ancillary works at Chitaura piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000404/2025-2026 | 2362/RD/PHE | 25/08/2025 | 09/10/2025 | MILAN GHOSH | 61.51 | 0 | 0 | 0
Total | [13 empty] | 13098.95 | 0 | 0