## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra | Raiganj Division | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14168 | New | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 2268/RD | 03/08/2023 | 03/08/2023 | Resource Division | 49.81 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Chopra | Malda Mechanical | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14168 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dangra Dangri Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016572) | Assistant Engineer - I | Junior Engineer-02 | ORD/000482/2023-2024 | 2489/MLMD | 04/08/2023 | 21/11/2025 | DEY ENTERPRISE.. | 26.44 | 19.12 | 72.31 | 72
3 | UTTAR DINAJPUR | Chopra | Raiganj Division | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14168 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 7213.93 | 119.8 | 1.66 | 30
4 | UTTAR DINAJPUR | Chopra | Raiganj Division | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14168 | New | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at DANGRA DANGRI .PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000031/2025-2026 | 1210/RD/PHE | 25/04/2025 | 09/06/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 61.96 | 0 | 0 | 0
Total | [13 empty] | 7352.13 | 138.92 | 1.89