## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KOKRA Piped Water Supply Scheme | SM/14175 | New | Material Requisition To Resource Division |  |  | RTOR000150/2022-2023 | 863/RD/PHE | 25/03/2023 | 25/03/2023 | Resource Division | 33.6 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KOKRA Piped Water Supply Scheme | SM/14175 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Kokra, 2.Bishahar, 3. Dhoabishua in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000290/2022-2023 | 539/RD/PHE | 22/02/2023 | 13/11/2024 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 65
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | KOKRA Piped Water Supply Scheme | SM/14175 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Kokra, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03540/2023-2024 | BP-2023-24-567 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 0.54 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | KOKRA Piped Water Supply Scheme | SM/14175 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Kokra, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03541/2023-2024 | BP-2023-24-568 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 0.65 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KOKRA Piped Water Supply Scheme | SM/14175 | New | Implementation of KOKRA and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000321/2022-2023 | 557/RD/PHE | 23/02/2023 | 27/04/2026 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 264.99 | 0 | 0 | 5
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | KOKRA Piped Water Supply Scheme | SM/14175 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Kokra Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018226) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000517/2023-2024 | 2513/MLMD | 04/08/2023 | 24/02/2026 | PABITRA MANDAL | 25.41 | 0 | 0 | 89
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KOKRA Piped Water Supply Scheme | SM/14175 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Kokra PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000446/2024-2025 | 3758/RD/PHED | 18/12/2024 | 18/03/2025 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 24.91 | 0 | 0 | 0
Total | [13 empty] | 429.7 | 0 | 0