## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | JAMIRA Piped Water Supply Scheme | SM/14179 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jamira Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017295) | Assistant Engineer - I | Junior Engineer-02 | ORD/000415/2023-2024 | 2444/MLMD | 04/08/2023 | 26/06/2026 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD.. | 29.24 | 16.11 | 55.11 | 55
2 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | JAMIRA Piped Water Supply Scheme | SM/14179 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 26/08/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 227.03 | 1.76 | 35
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | JAMIRA Piped Water Supply Scheme | SM/14179 | New | Material Requisition To Resource Division |  |  | RTOR000183/2022-2023 | 983/RD/PHE | 30/03/2023 | 30/03/2023 | Resource Division | 41.55 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | JAMIRA Piped Water Supply Scheme | SM/14179 | New | Quotation for new service connection at JAMIRA PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00240/2024-2025 | BP-2024-25-83 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 13.49 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | JAMIRA Piped Water Supply Scheme | SM/14179 | New | Quotation for new service connection at JAMIRA PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00629/2024-2025 | BP-2024-25-125 | 25/04/2024 | 25/04/2024 | W.B.S.E.D.C.LTD | 12.06 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | JAMIRA Piped Water Supply Scheme | SM/14179 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Jamira Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000284/2025-2026 | 1806/RD/PHE | 24/06/2025 | 21/12/2025 | AJIT PRAMANIK | 33.59 | 0 | 0 | 0
Total | [13 empty] | 13061.01 | 243.14 | 1.86