## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Providing functional house hold tap connection at village-Dubel Babhania & Purba Goalgaon of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000415/2022-2023 | 770/RD/PHE | 17/03/2023 | 16/05/2023 | UJJAL KUMAR SARKAR KUMARUJJAL51@GMAIL.COM | 11.13 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Construction of OHR(Capacity-250 cum) HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000507/2022-2023 | 850/RD/PHE | 24/03/2023 | 24/12/2023 | BHOWMICK ENTERPRISE | 91.89 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 1220/RD/PHE | 02/05/2023 | 02/05/2023 | Resource Division | 36.73 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Hemenpur PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000162/2024-2025 | 2896/RD/PHE | 25/09/2024 | 25/10/2024 | M/S SANJIB BHATTACHARJEE | 6.83 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Construction of Boundary Wall & pump House at 2nd Tube-well Site of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000410/2022-2023 | 765/RD/PHE | 17/03/2023 | 16/05/2023 | M/S BRIGHT CONSTRUCTION | 11.26 | 9.62 | 85.37 | 100
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Construction of Boundary Wall and pump House at Head work Site of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000483/2022-2023 | 822/RD/PHE | 22/03/2023 | 21/05/2023 | SAMRAT BOSE | 24.86 | 22.92 | 92.18 | 95
7 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Quotation for new service connection at HEMENPUR PH-II (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14180) |  |  | BILL/00743/2024-2025 | BP-2024-25-215 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 9.21 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Quotation for new service connection at HEMENPUR PH-I (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14180) |  |  | BILL/00742/2024-2025 | BP-2024-25-214 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 4.21 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Lahutara, 2. Hemenpur, 3. Basudebpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000295/2022-2023 | 541/RD/PHE | 22/02/2023 | 08/04/2023 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 61.71 | 0 | 0 | 60
10 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Providing functional house hold tap connection of Village-Hemenpur of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000543/2022-2023 | 955/RD/PHE | 29/03/2023 | 27/11/2024 | APEX ENTERPRISES RUPESH.RNJ@GMAIL.COM | 11.81 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Providing functional house hold tap connection at village-Paschim Goalgaon & Chengatuli of HEMENPUR Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000525/2022-2023 | 875/RD/PHE | 27/03/2023 | 01/08/2024 | SANDIP SARKAR | 11.81 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Hemenpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017332) | Assistant Engineer - I | Junior Engineer-02 | ORD/000558/2023-2024 | 2505/MLMD | 04/08/2023 | 26/03/2025 | SHREE BISHNU CONSTRUCTION | 24.48 | 20.78 | 84.9 | 89
13 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Laying of Additional pipeline with other ancillary works at different mouzas of HEMENPUR PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000378/2024-2025 | 3497/RD/PHE | 02/12/2024 | 02/03/2025 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 53.33 | 0 | 0 | 0
14 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Laying of pipeline main at village-Paschim Goalgaon and Chengatuli of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000516/2022-2023 | 870/RD/PHE | 27/03/2023 | 29/05/2024 | SAHA CONSTRUCTION SAHAKUMARESH51@GMAIL.COM | 35.44 | 32.76 | 92.43 | 85
15 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Laying of pipeline at village-Bhagabanpur of Hemenpur Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000533/2022-2023 | 945/RD/PHE | 29/03/2023 | 16/03/2025 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 32.21 | 28.54 | 88.61 | 100
16 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Providing functional house hold tap connection at village- Bhagabanpur of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000538/2022-2023 | 950/RD/PHE | 29/03/2023 | 25/01/2025 | M/S.SADHANA ENTERPRISE | 11.91 | 0 | 0 | 90
17 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Laying of Rising Main of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000102/2023-2024 | 2048/RD/PHE | 19/07/2023 | 01/02/2025 | M/S SAHA CONSTRUCTION | 4.31 | 0 | 0 | 100
18 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Laying pipe line at village- Purba Goalgaon of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000405/2022-2023 | 760/RD/PHE | 17/03/2023 | 16/05/2023 | M/S CHOUDHURY CONSTRUCTION KUMARCHOUDHURYSAMIR0@GMAIL.COM | 34.85 | 32.44 | 93.09 | 95
19 | UTTAR DINAJPUR | Karandighi | Raiganj Division | HEMENPUR Piped Water Supply Scheme | SM/14180 | New | Laying distribution of pipe line of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000465/2022-2023 | 816/RD/PHE | 22/03/2023 | 06/05/2023 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 35.97 | 29.89 | 83.08 | 100
Total | [13 empty] | 513.97 | 176.94 | 34.43