## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RANIGANJ Piped Water Supply Scheme | SM/14181 | New | Material Requisition To Resource Division |  |  | RTOR000155/2022-2023 | 887/RD/PHE | 27/03/2023 | 27/03/2023 | Resource Division | 73.71 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RANIGANJ Piped Water Supply Scheme | SM/14181 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Raniganj, 2. Alianagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000296/2022-2023 | 542/RD/PHE | 22/02/2023 | 11/11/2024 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 51.42 | 0 | 0 | 80
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | RANIGANJ Piped Water Supply Scheme | SM/14181 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Raniganj Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017338) | Assistant Engineer - I | Junior Engineer-02 | ORD/000535/2023-2024 | 2529/MLMD | 04/08/2023 | 27/01/2026 | HANNAN BUILDERS PVT. LTD. | 36.8 | 28.89 | 78.5 | 79
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RANIGANJ Piped Water Supply Scheme | SM/14181 | New | Implementation of RANIGANJ and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000359/2023-2024 | 2475/RD/PHE | 24/08/2023 | 07/05/2025 | UJJWAL DAS | 509.3 | 144.48 | 28.37 | 80
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | RANIGANJ Piped Water Supply Scheme | SM/14181 | New | Quotation for new service connection at RANIGANJ PH-I (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00222/2024-2025 | BP-2024-25-82 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 3.31 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | RANIGANJ Piped Water Supply Scheme | SM/14181 | New | Quotation for new service connection at RANIGANJ PH-II (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00221/2024-2025 | BP-2024-25-81 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 8.25 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | RANIGANJ Piped Water Supply Scheme | SM/14181 | New | Quotation for new service connection at RANIGANJ PH-III (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00220/2024-2025 | BP-2024-25-80 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 7.5 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RANIGANJ Piped Water Supply Scheme | SM/14181 | New | Construction of concrete pathway ,Land development and other ancillary works for RANIGANJ Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000500/2024-2025 | 45/RD/PHE | 03/01/2025 | 16/08/2025 | GULJAN BEGAM | 22.31 | 0 | 0 | 60
Total | [13 empty] | 712.61 | 173.37 | 24.33